# 2.  Scope  Snapshot

The Cleris Pulse platform is an AI-powered data-understanding tool. Users upload CSV data sources; the platform auto-generates per-source guidelines describing the data; users then ask plain-language questions and receive a streamed natural-language answer, an auto-generated dashboard, and follow-up question suggestions. SQL is generated in the background across a multi-stage API architecture where each endpoint feeds the next.

We are not building the platform. We are building the independent evaluation layer that measures how well it answers questions — and proves that measurement is reproducible across releases.

| Dimension | Confirmed position |
| --- | --- |
| What we build | Golden synthetic datasets, verified Q&A evaluation pairs, an LLM-as-Judge scoring module, and a regression scorecard. Evaluation Orchestrator is designed but not built (see Section 12). |
| Domains | Five, locked. CRM → Sales → Finance → Project Management → Logistics. CRM built first. No additional domains this phase. |
| Volume | 750+ verified Q&A pairs across all five domains (internal build target 800). Maximum 250,000 rows per table. No cap at domain level. |
| Quality bar | ≥95% deterministic exact-match across all five domains before any final handover. Numeric answers must be identical on repeat runs. |
| Environments | Staging and QA only. No production access is requested, granted, or used at any point. |
| Platform models | Claude Sonnet for responses; Gemini Flash Lite for guideline and instruction generation. Model switching per stage exists but stays unused until accuracy is baselined. |
| Data flow | All evaluation runs submit questions through the Pulse API. Nothing runs standalone. Any model comparison happens through Pulse’s own model-switching architecture. |
| Delivery shape | Staggered per-domain release with named dates — not a single Week 10 drop. First domain available for client validation inside the Week 2–5 window. |
| Timeline | 10 weeks from kickoff, landing mid-October 2026. |

# 3.  Source Hierarchy and Changes

## 3.1  Precedence order

| Rank | Source | Authority |
| --- | --- | --- |
| 1 | Customer Alignment Minutes (August 2026) | Highest. Records what the client actually agreed. Overrides everything below on any point of scope, volume, or constraint. |
| 2 | LLM Engineer Scope Document v2.0 | Technical interpretation of the minutes. Authoritative on component design. |
| 3 | This Execution Specification v3.0 | Authoritative on how the work is built, sequenced, reviewed, and accepted. Resolves gaps left by 1 and 2. |
| 4 | Technical & Commercial Proposal v2.1 | Commercial baseline only. Superseded on all technical detail. Do not build from it. |

## 3.2  Material changes from Proposal v2.1 — read before building

| # | Item | Proposal v2.1 said | Confirmed position | Build impact |
| --- | --- | --- | --- | --- |
| C1 | Domain list | Device Management, IT Ops/Incidents, CRM/Sales, E-Commerce, Finance/GL | CRM, Sales, Finance, Project Management, Logistics — locked, CRM first | Discard all proposal domain schemas and table lists. Rebuild from Section 6. |
| C2 | Numeric tolerance | exact_match with ±2% numeric tolerance | Numerics must be identical on repeat runs. Zero tolerance. Any numeric variance is a fail. | Remove the tolerance parameter from the scorer entirely. Do not make it configurable. |
| C3 | Evaluation Orchestrator | Full build, Phase 4, a priced deliverable | DEFERRED pending the client’s internal eval-tool demo. Design only. | Do not write orchestrator implementation code. Produce the architecture document only (Section 12). |
| C4 | Timeline | 10–12 weeks | 10 weeks fixed | No 11th or 12th week of contingency exists. Sequence accordingly. |
| C5 | Q&A volume | Not stated as a total | 750+ verified pairs across five domains | Per-domain quotas are now fixed. See Section 9.1. |
| C6 | Row volume | Not stated | Hard cap 250,000 rows per table; no domain-level cap | Generation pipeline needs an enforced cap check before export. |
| C7 | Tier mix | T4 25%, T5 = GROUP BY + HAVING at 10% | T4 20%, T5 = semantic/contextual logic at 15% | T5 is no longer a SQL pattern tier. It tests reasoning: ranked lists, comparisons, trend language. |
| C8 | Platform coupling | "Pulse architecture-aware design"; CSV headers aligned to Pulse ingestion | Platform agnosticism is a hard design constraint. Datasets must produce comparable results on any NLQ tooling. | The single largest change. Nothing Pulse-specific may be encoded in schema, naming, or join design. |
| C9 | Delivery shape | Batch: domains 1–3 Week 4, domains 4–5 Week 5 | Staggered per-domain with named dates; CRM validated first | Release calendar in Section 16.2 replaces the batch plan. |
| C10 | Date tolerance | ±1 day tolerance carried in earlier scoring drafts | Not carried forward. Date values returned as answers are facts and compare exactly. | Flagged for written client confirmation — see OI-3, Section 23. |

# 4.  Hard Design Constraints

These were confirmed as non-negotiable in the customer alignment session. Every design and implementation decision is checked against them. A deliverable that violates one of these is rejected regardless of its accuracy.

HC-1 · No PII — absolute All datasets are 100% synthetic. No real customer data, no anonymised real data, no derived personal fields, no scraped or sampled real-world entity names. Where a domain needs a field that could imply identity — name, email, address, phone, account number, government ID — it is Faker-generated with no real-world mapping. - Failure mode to avoid: seeding Faker from a real customer list to make data "look right". Do not do this under any circumstance. - Check: every generator module declares its identity-adjacent fields in a header comment, and the QA reviewer confirms each one is Faker-sourced.

HC-2 · Platform agnosticism The golden datasets must produce comparable evaluation results on any NLQ tooling, not only on the Pulse backend. This was raised by the client engineering team and accepted by the Platform Owner. Schema design, column naming, and join architecture must be tool-neutral. If a different NLQ system ingested the same CSVs, it should be able to answer the same questions and return the same numbers. - Do not encode assumptions about Pulse’s SQL generation style, its ingestion quirks, or its guideline generator into the dataset structure. - Do not name a column to make Pulse parse it more easily. Name it the way a business analyst would name it. - Test: the ANSI-SQL reference query must run unmodified in DuckDB. If it needs a dialect-specific rewrite, the schema is wrong.

HC-3 · The non-determinism boundary Answer phrasing, response length, and dashboard styling MAY vary between runs of the same question. Do not fail a response for any of these. Numeric values MUST be identical on repeat runs of the same question. Any numeric variance is a fail. This boundary defines how the LLM-as-Judge module is calibrated: judge on substance and numerics, never on phrasing or format aesthetics.

HC-4 · Evaluations run through the Pulse backend Nothing evaluates standalone. Every Q&A evaluation run submits its question through the Pulse API. Any model comparison — for example Claude Sonnet against another model — happens through Pulse’s model-switching architecture, not by calling models directly. Corollary: our reference SQL execution in DuckDB is for ground-truth verification only. It is never the thing being scored.

HC-5 · Generated SQL must be captured and logged The Pulse API response includes the generated SQL; the Platform Owner has confirmed this is available. Every evaluation run logs the generated SQL per question so that a failure can be isolated to the SQL generation stage. Important scope boundary: SQL capture is for failure diagnosis only. Per-stage evaluation — scoring intent selection or SQL generation independently — is explicitly out of scope.

HC-6 · Non-production access only Staging and QA environments only, for the whole engagement. Do not request, accept, or use production credentials. If a client-side contact offers production access to unblock something, decline and escalate to the Engagement Lead. This is not a judgement call for an individual engineer.

HC-7 · Reproducibility A clean-room re-run from the committed seed must produce byte-identical CSV output. The client may re-run our scripts at any time. This forbids: unseeded randomness, wall-clock or "today" values baked into data, dictionary/set iteration order dependence, parallel generation that does not fix its own ordering, and any network call inside the generation path.

# 5.  Component Architecture and Build Priority

Five build tracks. They are listed in strict priority order. Tracks A and B are the gate for the entire engagement — everything else depends on them being accurate, well-structured, and accepted by the Platform Owner.

| Track | Component | Priority | Gate condition | Primary output |
| --- | --- | --- | --- | --- |
| A | Golden Evaluation Datasets | P1 — build first | Nothing downstream starts until the CRM dataset is generated, integrity-checked, and accepted | 3–5 relational CSV files per domain, ≤250K rows per table, with data dictionary |
| B | Q&A Evaluation Pair Sets | P1 — concurrent with A, per domain | A domain’s dataset must be frozen before its Q&A authoring starts. No authoring against a moving schema. | 750+ pairs, 7-field CSV per domain, SQL-verified |
| C | LLM-as-Judge Module | P2 | Requires judge_reference answers from B and calibration anchors | Python module + per-domain JSON config + rubric PDF |
| D | Regression Scorecard | P3 | Requires scored output from C | CSV (CI/CD-ready) + PDF summary per run |
| E | Evaluation Orchestrator | DEFERRED | Blocked pending the client’s internal eval-tool demo and the augment-versus-migrate decision | Architecture document and config contract only — no implementation |

The dependency that governs the whole schedule A domain’s schema must be frozen before its Q&A pairs are authored, because every pair embeds a reference SQL query bound to specific table and column names. A late schema change invalidates every pair already written against it. Practical rule: once a domain dataset is exported and hashed into manifest.json, its schema is frozen. Changes after that point go through a documented re-issue, not an edit in place.

# 6.  Domains, Build Order and Schema Targets

Five domains, confirmed and locked in the customer alignment session. The Platform Owner explicitly preferred five fully tuned domains over ten partially useful ones. CRM is built first, confirmed by both Platform Owner contacts, on the basis that CRM is the most common use case for their major customer segment.

| # | Domain | Tables (3–5) | Join & aggregation emphasis | Imperfection focus | Dataset due | Q&A due |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | CRM [FIRST] | contacts, accounts, opportunities, activities, interactions | Opportunity↔Account INNER JOIN; activity COUNT per rep; deal-stage aggregation; contact→account LEFT JOIN | Duplicate contacts; NULL close dates | Fri 28 Aug | Fri 4 Sep |
| 2 | Sales | leads, deals, products, quotations, targets | Deal↔Product INNER JOIN; quota attainment SUM; 3-table Lead→Deal→Product | Missing product prices; duplicate deal lines | Fri 4 Sep | Fri 11 Sep |
| 3 | Finance | accounts, transactions, ledger_entries, budgets, fx_rates | Transaction↔Ledger LEFT JOIN; FX-adjusted SUM; budget vs actual; rolling balance | NULL FX rates; boundary-date transactions. Numeric precision critical. | Fri 11 Sep | Fri 18 Sep |
| 4 | Project Management | projects, tasks, milestones, resources, time_entries | Task↔Resource INNER JOIN; milestone completion %; 3-table Project→Task→Time_Entry | Boundary dates; overlapping/open-ended date ranges. Date logic complex. | Fri 18 Sep | Fri 25 Sep |
| 5 | Logistics | shipments, orders, carriers, warehouses, inventory | Shipment↔Carrier INNER JOIN; Order↔Warehouse LEFT JOIN; 3-table Order→Shipment→Carrier | Duplicate shipment records by design; orphaned orders | Fri 18 Sep | Fri 25 Sep |

## 6.1  Domain-specific engineering notes

- CRM — this is the reference implementation. Every convention in Sections 7 and 8 is proven here first, and the other four domains inherit the pattern. Budget more time for CRM than its size suggests: you are building the framework, not just a dataset.

- Finance — the highest-risk domain for the zero-tolerance numeric rule. FX conversion, rounding order, and ledger sign conventions all create float drift. Use fixed-point decimal internally, define rounding once, apply it identically in the generator and in every reference query.

- Project Management — the highest-risk domain for ambiguous questions. "Overdue", "in progress", and "this quarter" all need explicit definitions written into the data dictionary before any Q&A pair uses them.

- Logistics — duplicate shipment records are intentional here, which means duplicate-sensitive aggregations (COUNT vs COUNT DISTINCT) are the point of this domain, not an accident to be cleaned up.

- Sales — overlaps conceptually with CRM. Enforce the cross-domain uniqueness rule strictly: no question may appear in both. Differentiate by entity focus (Sales is deal/product/quota-centric; CRM is account/contact/activity-centric).

# 7.  Data Generation Standard

## 7.1  Stack and pinning

| Element | Standard |
| --- | --- |
| Language | Python 3.11 |
| Core libraries | numpy · Faker 24.x · pandas 2.x · DuckDB 0.10 |
| Quality tooling | SQLFluff (DDL and reference SQL linting) · ruff + black (Python) · pytest |
| Randomness | numpy.random.default_rng(seed=42) as the root generator. Faker seeded from the same root. |
| Dependency pinning | requirements.txt with exact pins committed. No unpinned or range-pinned dependencies. |
| Version tagging | Git LFS; repository tagged dataset-v1.0.0 at first accepted release, incrementing per re-issue. |

## 7.2  Determinism rules

The seed alone does not guarantee reproducibility. These rules do.

- One root RNG, seeded at 42, committed to version control. Derive a per-table child generator from it deterministically (for example by spawning in a fixed table order) so that adding a table does not shift the values in existing tables.

- Faker instances are seeded from the same root. Never instantiate an unseeded Faker.

- No wall-clock reads inside the generation path. "Today" is a configuration constant, not datetime.now(). Fix it per dataset version and record it in the manifest.

- No parallelism unless the merge order is explicitly sorted afterwards. Thread scheduling is not deterministic.

- No iteration over unordered containers where the order affects output. Sort keys explicitly.

- No network calls in the generation path. Ever.

- Serialise with fixed float formatting and fixed column order so byte-identical output is achievable.

## 7.3  Row volume targets

The 250,000-row cap is a hard limit, not a target. Accuracy is priority one and cost optimisation is explicitly deferred, but oversized tables make DuckDB verification slow and make failures harder to diagnose. Generate to the smallest size that still exercises the distributions honestly.

| Table role | Target rows | Rationale |
| --- | --- | --- |
| Reference / lookup (carriers, fx_rates, products) | 50 – 5,000 | Cardinality matters more than volume; keeps join fan-out interpretable |
| Dimension (accounts, contacts, projects, warehouses) | 5,000 – 50,000 | Enough for meaningful GROUP BY cardinality without slowing verification |
| Fact / transactional (transactions, activities, time_entries, shipments) | 100,000 – 250,000 | Exercises aggregation robustness and long-tail distributions; respects the hard cap |

- The generation CLI exposes a --profile flag: dev (1% scale, for fast iteration) and full (delivery scale). Both are seeded identically; only the row count differs.

- Never deliver dev-profile output. The export step refuses to write to the release directory unless --profile full is set.

- A pre-export assertion fails the build if any table exceeds 250,000 rows.

## 7.4  Statistical distributions

| Field type | Distribution | Parameters | What it buys us |
| --- | --- | --- | --- |
| Revenue / sales amounts | Pareto | α = 1.16 | Realistic long-tail revenue; makes SUM and AVG diverge meaningfully, and makes outlier handling observable |
| Event frequency | Poisson | λ = 3.2 | Average 3.2 events per entity per period; produces natural COUNT variance per group |
| Date clustering | Gaussian mixture | 3 components | Seasonal quarter-end spikes over a flat baseline; makes period-filtered questions non-trivial |
| NULL injection | Bernoulli | p = 0.025 | 2–3% NULL rate on nullable fields; drives LEFT JOIN and NULL-handling behaviour |

## 7.5  Controlled imperfections

All four types are required in every dataset. They are the reason this benchmark is harder than a clean synthetic set, and they are what the client is paying for.

| Type | Rate | Implementation rule |
| --- | --- | --- |
| Duplicate rows | ~1% | Near-duplicates: the same logical entity with slightly varied field values. Not byte-identical copies — those are trivially detectable and test nothing. |
| Missing values | 2–3% | Bernoulli injection (p = 0.025) on nullable fields only. Never null a primary key or a foreign key participating in a declared INNER JOIN path. |
| Outlier records | 0.5% | Extreme numeric values, injected after the base distribution is drawn so the base distribution stays clean and describable. |
| Boundary dates | Deterministic set | 1900-01-01, 2038-01-19, a far-future date, and the fixed current-day constant. Injected at known row positions and documented in the data dictionary. |

The imperfection rule that breaks benchmarks if you get it wrong Ground-truth answers are computed from the data as delivered — imperfections included. If a table has 1% duplicate rows, the correct answer to "how many accounts are there" includes those duplicates unless the question explicitly says distinct. Never compute an expected answer against a pre-imperfection intermediate dataframe. Compute it by executing the reference SQL against the exported CSV, and only against the exported CSV. This is the single most common way a golden dataset silently becomes wrong.

## 7.6  Referential integrity gate

- DuckDB PRAGMA foreign_key_check must pass before any CSV file is exported. This is a gate, not a report — a failure stops the export.

- Orphaned rows are permitted only where a domain deliberately requires them (for example Logistics orphaned orders). Where permitted, they are declared in the schema definition and excluded from the check by explicit configuration, never by disabling the check.

- Every declared INNER JOIN path is asserted non-empty; every declared LEFT OUTER JOIN path is asserted to produce at least one unmatched row. A join path that cannot demonstrate its own semantics is not a join path.

## 7.7  Packaging and manifest

- SHA-256 hash of every exported CSV recorded in manifest.json alongside row count, column count, generation timestamp, seed, library versions, and the fixed "today" constant.

- manifest.json is the reproducibility contract. A clean-room re-run regenerates it and the hashes must match exactly.

- Release artefacts are immutable. A correction produces dataset-v1.0.1, never an edit to v1.0.0.

# 8.  Schema and Naming Conventions

These conventions exist to satisfy HC-2 (platform agnosticism). They are deliberately boring: a naming scheme that surprises nobody is a naming scheme that any NLQ tool can handle. Agree the concrete headers with the Platform Owner DRI before generation begins, but bring these conventions to that session as the proposed default rather than starting from a blank page.

| Convention | Rule | Example |
| --- | --- | --- |
| Table names | lower snake_case, plural, no domain prefix | opportunities, ledger_entries, time_entries |
| Primary keys | singular table name + _id | account_id, shipment_id |
| Foreign keys | identical to the referenced primary key name | opportunities.account_id → accounts.account_id |
| Dates | _date for calendar dates, _at for timestamps | close_date, created_at |
| Booleans | is_ or has_ prefix, values true/false lowercase | is_active, has_renewal |
| Amounts | _amount suffix, with a sibling currency_code where multi-currency | deal_amount, currency_code |
| Status / category | singular noun, no abbreviation | stage, status, region — not stg, sts, rgn |
| Character set | ASCII only, no spaces, no unicode, no reserved SQL words | Avoid: order, group, from, "Close Date" |
| Header row | CSV header text is byte-identical to the DDL column name | No display-friendly headers in the CSV |

## 8.1  CSV file format contract

| Property | Standard |
| --- | --- |
| Encoding | UTF-8, no BOM |
| Quoting | RFC 4180. Quote only when required (delimiter, quote, or newline present). |
| Line endings | LF (\n), consistent across all files |
| Dates | ISO 8601 — YYYY-MM-DD for dates, YYYY-MM-DDTHH:MM:SS for timestamps, no timezone suffix |
| Decimals | Period separator, no thousands separator, fixed decimal places per column as declared in the data dictionary |
| NULL representation | Empty field (nothing between delimiters). Empty string is never used as a meaningful value — if a column needs "blank" as a real category, it uses an explicit token declared in the dictionary. |
| Booleans | Lowercase true / false |
| Column order | Fixed and identical to the DDL; primary key first |

## 8.2  Join architecture

- 3–5 related tables per domain with 1:N relationships mandatory; N:M via bridge tables where domain-realistic.

- The Platform Owner has confirmed primary keys exist across tables — build joins against the referenced key structure.

- INNER JOIN and LEFT OUTER JOIN paths validated before data generation begins, not discovered afterwards.

- Shortcut prevention: for tiers T2 through T5, the schema must make it impossible to answer the question correctly from a single table. If a denormalised convenience column would let a model skip the join, remove that column.

- Minimum 2-hop join depth applies to T2–T5 questions. T1 is a deliberate single-table control tier — see OI-1 in Section 23, which flags this apparent conflict for written client confirmation.

## 8.3  ER diagrams

- One ER diagram per domain, produced before generation and approved before generation. dbdiagram.io source committed to the repo alongside the exported PDF, so the diagram is version-controlled text rather than an image nobody can edit.

- Each diagram annotates: PK/FK pairs, cardinality, which join paths are INNER versus LEFT, and where imperfections are injected.

# 9.  Q&A Evaluation Pair Specification

## 9.1  Volume plan

Contract floor is 750+ verified pairs across all five domains. Build target is 800 — a deliberate ~7% buffer, because pairs that fail the independent audit are reworked rather than removed, and some will not survive rework.

| Tier | Share | Per domain | All 5 domains |
| --- | --- | --- | --- |
| T1 — single-table aggregation | 20% | 32 | 160 |
| T2 — INNER JOIN (2 tables) | 25% | 40 | 200 |
| T3 — LEFT OUTER JOIN (2 tables) | 20% | 32 | 160 |
| T4 — 3-table JOIN + aggregation | 20% | 32 | 160 |
| T5 — semantic / contextual logic | 15% | 24 | 120 |
| TOTAL | 100% | 160 | 800 |

## 9.2  Tier taxonomy

| Tier | Type | SQL pattern | Scoring |
| --- | --- | --- | --- |
| T1 | Single-table aggregation | SELECT SUM / COUNT / COUNT(DISTINCT col) FROM tbl WHERE cond | Deterministic exact_match; numerics identical on repeat runs |
| T2 | INNER JOIN, 2 tables | SELECT cols FROM t1 INNER JOIN t2 ON t1.pk = t2.fk WHERE cond | Deterministic exact_match |
| T3 | LEFT OUTER JOIN, 2 tables | SELECT cols FROM t1 LEFT JOIN t2 ON t1.pk = t2.fk | exact_match plus explicit NULL-handling check |
| T4 | 3-table JOIN + aggregation | SELECT SUM/COUNT FROM t1 JOIN t2 JOIN t3 GROUP BY col | Deterministic exact_match |
| T5 | Semantic / contextual logic | Reasoning beyond direct aggregation — ranked lists, period-over-period comparisons, trend language | LLM-as-Judge primary; exact_match on every numeric component |

T5 is not a harder SQL tier The proposal defined T5 as GROUP BY + HAVING. That is now T4 territory. Confirmed T5 tests whether the platform can reason: "which three regions grew fastest last quarter", "is the pipeline healthier than it was six months ago", "which accounts are at risk". A T5 pair still has a deterministic numeric core — the ranking, the percentages, the counts — and those still compare exactly. The judge scores the surrounding reasoning; the scorer scores the numbers.

## 9.3  Q&A CSV format — seven fields per pair

This is a contracted format. Do not add, remove, or rename fields. Internal metadata lives in a separate companion file (Section 9.5).

| Field | Description | Authoring rule |
| --- | --- | --- |
| natural_language_question | The exact question submitted to the platform API | Phrased as a business user would phrase it. No SQL vocabulary, no column names, no hints about which tables to join. |
| expected_answer | Deterministic ground-truth answer | Numeric values exact on all repeat runs. Format declared and consistent within a tier. Produced by executing reference_sql against the exported CSVs — never hand-computed. |
| reference_sql | The SQL query producing expected_answer | ANSI SQL, SQLFluff-clean, runs unmodified in DuckDB. Must be captured and logged per question. |
| reference_tables | All tables required by the query | Names match the platform data source names exactly. |
| reference_fields | All fields referenced in the query | Fully qualified table.column. Include join keys and filter fields, not just projected columns. |
| judge_reference | Model-level reference answer used as the LLM-as-Judge anchor | The ideal full contextual response — what an excellent answer looks like in substance. Written to describe content, not a phrasing to be matched. |
| derivation_rationale | Step-by-step explanation of how the answer is computed | Written so a reviewer can verify the logic without reading the SQL. This is what makes an audit finding actionable. |

## 9.4  Authoring rules

- Every pair is verified by executing its reference_sql in DuckDB against the exported CSV files — not against an in-memory dataframe, and not against a pre-imperfection intermediate.

- No question is duplicated across domains. Enforced by a normalised-text hash check across the full corpus, run in CI.

- Questions must exercise the injected imperfections. If a domain has NULL FX rates, at least one pair must depend on how those NULLs are handled. Otherwise the imperfection engineering is decorative.

- Every question has exactly one defensible answer. If two reasonable readings give different numbers, the question is ambiguous — either rewrite it or move it to the ambiguity set (Section 9.5), never ship it as deterministic.

- Business vocabulary in the question, technical vocabulary in the rationale. "How much did we close last quarter" — not "SUM deal_amount where stage equals Closed Won".

- Vague temporal language must be grounded. "Last quarter" resolves against the fixed "today" constant, and the resolution is stated in derivation_rationale.

- Answer format is declared per tier and held consistent: scalar for T1 aggregations, ordered list for rankings, table for multi-column results.

- The judge_reference is authored at the same time as the pair, not retrofitted later. Retrofitted references drift toward whatever the platform happened to output.

- No pair is authored against an unfrozen schema.

- The author of a pair never audits it. Independent review is a hard rule (Section 15).

## 9.5  Ambiguity handling and rephrase testing

An NLQ system that answers one phrasing correctly and a synonym incorrectly is not production-ready. We test this explicitly. Because the delivered Q&A CSV is a contracted 7-field format, ambiguity metadata lives in a companion file — rephrase_map.csv — which links pairs by a pair_group_id without altering the delivered schema.

| Class | What it tests | Construction |
| --- | --- | --- |
| Temporal | Consistent resolution of relative time expressions | Same underlying query asked as "last quarter", "Q2", and an explicit date range — all three must return identical numerics |
| Lexical | Synonym robustness | "revenue" / "sales" / "closed value" over the same measure |
| Referential | Entity reference resolution | Named entity, pronoun-style follow-up, and category reference resolving to the same rows |
| Rephrase | Surface-form invariance | Question restated in a different grammatical structure with no semantic change |

- Target: roughly 10% of each domain’s pairs belong to a rephrase group of two or more variants.

- Scoring rule for a rephrase group: every variant must return identical numerics. A group where variants disagree is a platform finding, reported in the scorecard drill-down — it is not a defect in our dataset.

## 9.6  Verification protocol

- Author writes the pair and its reference_sql.

- Automated runner executes every reference_sql against the released CSVs in a clean DuckDB instance and writes the result into expected_answer. Authors do not type answers by hand.

- Runner emits a verification log per domain: question id, SQL, row count returned, execution time, result hash.

- Any SQL returning zero rows, an error, or a NULL scalar where a number is expected is flagged and blocked from release.

- Independent reviewer re-executes the full set on a fresh instance from the released artefacts only (Section 15).

# 10.  LLM-as-Judge Scoring Module

The judge evaluates each platform response on four quality dimensions, calibrated per domain. Its purpose is to capture answer quality that exact-match cannot measure — completeness, coherence, contextual soundness — without penalising the variation the client has told us to expect.

| Dimension | What the judge assesses | Score scale |
| --- | --- | --- |
| Factual correctness | Does the answer match the expected answer in substance? Numeric values must be exact. | 5 = exact · 3 = partial · 1 = wrong |
| Completeness | Does the response include all required values and context from the Q&A pair? | 5 = complete · 3 = missing fields · 1 = severely incomplete |
| Format adherence | Is the answer in the expected format? Dashboard styling variation is explicitly not a failure. | 5 = correct · 3 = minor deviation · 1 = wrong format |
| SQL plausibility | Is the generated SQL syntactically valid and logically coherent for the question? | 5 = valid & correct · 3 = valid but suboptimal · 1 = invalid |

## 10.1  Build requirements

- Python module with Jinja2 judge prompt templates, calibrated against the non-determinism boundary.

- Per-domain JSON config: model selection, temperature, max tokens, retry policy, concurrency limit.

- Temperature 0 and a fixed seed where the provider supports it. A judge that is itself non-deterministic cannot certify determinism.

- Async LLM call batching with backoff to manage provider rate limits.

- Full prompt and full raw response logged per scored item, with a stable judge_run_id. A score without its reasoning trace is not auditable.

- The judge receives the question, the platform response, the expected_answer and the judge_reference. It does not receive the reference_sql — SQL plausibility is assessed on the platform’s own generated SQL, and handing the judge the correct query invites leakage.

- Schema-validated structured output: four integer scores plus a rationale string per dimension. Malformed output is retried, then failed loudly — never silently coerced.

## 10.2  Calibration protocol

- Assemble at least 10 human-graded anchor examples per domain, spanning the score range — not 10 easy passes.

- The Platform Owner team participates in the CRM calibration session (scheduled Week 5). CRM calibration sets the pattern the other four domains inherit.

- Run the judge against the anchors blind to the human scores.

- Acceptance: the judge is within ±1 of the human score on at least 90% of anchors per dimension, and never disagrees on direction (a human 5 scored as a 1 or 2, or the reverse) on any anchor.

- Where acceptance fails, revise the rubric and prompt — not the human grades — and re-run. Record each iteration.

- Calibration must complete before any production scoring run. Scores produced by an uncalibrated judge do not enter the scorecard.

Encoding the non-determinism boundary in the rubric The rubric must state explicitly, in the prompt: differences in wording, sentence length, ordering of prose, tone, and dashboard presentation are not deductions. Only substance and numeric accuracy are scored. Include worked negative examples in the prompt — a correct answer phrased very differently from the judge_reference, scored 5 — so the model sees what "do not penalise phrasing" means in practice.

# 11.  Regression Scorecard

Produced at the end of every evaluation run. It lets the Prime Contractor and the Platform Owner track accuracy across platform releases and catch regressions before they reach staging.

## 11.1  Summary output — one row per domain per run

| Column | Content |
| --- | --- |
| run_id, run_timestamp_iso | Unique run identifier and ISO 8601 timestamp |
| platform_version, dataset_version | Version tags for both sides of the comparison — a scorecard without both is uninterpretable |
| domain, tier | Reported per domain, and broken out per tier within domain |
| questions_total, exact_match_pass, exact_match_pct | Deterministic accuracy |
| judge_factual, judge_completeness, judge_format, judge_sql, judge_overall | Mean judge score per dimension, reported separately from exact-match — never blended into a single number |
| baseline_exact_match_pct, delta_pct | Comparison against the established baseline |
| regression_flag | true where delta_pct ≤ -5.0 for any domain |

## 11.2  Question-level drill-down — one row per question

- question_id, domain, tier, natural_language_question

- expected_answer, actual_answer, exact_match_result

- platform_generated_sql — logged for every question, and mandatory for every failure so the client can trace the failure to a pipeline stage

- judge scores per dimension plus judge rationale

- rephrase_group_id where applicable, so within-group numeric disagreement is visible

## 11.3  Operating rules

- Baseline: the first scorecard run establishes the accuracy baseline for all future comparisons. It is recorded immutably, not recalculated.

- Regression flag: any domain dropping 5 percentage points or more from baseline triggers an automated flag.

- Output: structured CSV (machine-readable, CI/CD-ready) plus a PDF summary for human review.

- Exact-match accuracy and judge scores are always reported side by side and never combined into a composite score. They measure different things and the client uses them differently.

# 12.  Evaluation Orchestrator — Deferred

Status: DEFERRED — do not build The Platform Owner flagged that the end client already has an internal evaluation tool and did not recall the Orchestrator being central to the agreement. Decision deferred: the end client will demo their internal eval tool, after which both sides decide whether TechM augments it or the end client migrates to the TechM Orchestrator. Action now: produce a high-level design and architecture document. Do not write implementation code until the datasets and Q&A pairs are accepted AND the tooling decision is resolved.

## 12.1  What to produce during the deferral

- Architecture document: component diagram, data flow, failure and retry model, where deterministic scoring sits relative to judge scoring.

- Config contract: the single YAML/JSON file that would parameterise the whole tool — endpoint, auth method, request shape, response field mapping, question format, timeouts, concurrency.

- Interface definition for the scoring and scorecard modules, so that whichever tool ultimately drives the loop can call our scorer. This is the part that pays off regardless of the decision.

- A written comparison framework for the augment-versus-migrate decision, so that when the demo happens we can respond within days rather than starting the analysis then.

## 12.2  Requirements if it is ultimately built

- Parameter-driven: API endpoint, auth, question format, and response field names configurable via a single config file. Nothing hard-coded to the Pulse API structure.

- Platform-agnostic by construction — the same requirement as HC-2, applied to the tool rather than the data.

- Submits each question to the platform API and captures the full response payload including the generated SQL.

- Applies deterministic scoring (exact match, zero numeric tolerance) and passes responses to the LLM-as-Judge module.

- Writes a result CSV per run: question, expected, actual, generated_sql, det_score, judge_score, judge_rationale.

- Generates the per-domain accuracy summary that feeds the Regression Scorecard.

# 13.  Repository, Environment and Engineering Standards

## 13.1  Repository layout

nlq-eval-framework/

config/            per-domain generation + judge configs, schema definitions

generators/        seeded data generation, one module per domain

schemas/           DDL, ER diagram sources (dbdiagram.io), CSV header spec

qa_pairs/          authoring templates, Jinja2 SQL library, verification runner

judge/             LLM-as-Judge module, prompt templates, calibration anchors

scorecard/         scoring, aggregation, CSV + PDF report generation

orchestrator/      DESIGN ONLY — architecture doc and config contract, no build

tests/             pytest suites, integrity assertions, property tests

release/           versioned outputs, manifest.json (Git LFS)

docs/              data dictionaries, rubric, audit reports, KT material

## 13.2  Standards

| Area | Standard |
| --- | --- |
| Branching | Trunk-based. Short-lived feature branches, merged via pull request. No direct commits to main. |
| Review | One reviewer minimum. Anything touching data generation or reference SQL requires a reviewer who is not the author — this is the same independence rule as the QA audit, applied continuously. |
| Linting | ruff + black for Python; SQLFluff for all DDL and reference SQL. CI fails on lint errors. |
| Testing | pytest. Unit tests for every generator. Property tests asserting FK integrity, row caps, imperfection rates within tolerance, and null-rate bounds. |
| CI checks | Lint · tests · FK integrity gate · row-cap assertion · cross-domain question uniqueness hash · manifest hash regeneration |
| Large files | Git LFS for all released CSVs. Never commit a full-scale CSV outside LFS. |
| Secrets | No credentials in the repository, ever. .env.example is committed; .env is not. Client-issued credentials stay in the approved store and never appear in code, logs, notebooks, screenshots, or tickets. |
| Logging | No response payload containing client data is written to a shared log. Evaluation logs contain our synthetic data and platform outputs about it — nothing else. |

## 13.3  Environment and access discipline

- Staging and QA only (HC-6). If an engineer finds themselves holding production credentials, stop and escalate immediately.

- Data drop location to be confirmed — the client has provided a Box link that currently requires internal access we do not have (see DEP-08, Section 19). Do not work around this with personal file sharing.

- Client-side onboarding to Apple Connect is a prerequisite for API access. The engineer list was due to the Prime Contractor by 5 August; confirm every engineer on the delivery team is on it.

# 14.  Definition of Done

## 14.1  Per-artefact

| Artefact | Done means |
| --- | --- |
| Domain dataset | ER diagram approved · DDL SQLFluff-clean · FK integrity gate passed · all four imperfection types present at target rates · row cap respected · SHA-256 in manifest.json · data dictionary written · clean-room re-run reproduces byte-identical output |
| Q&A pair set | Tier quotas met · every reference_sql executes clean in DuckDB against released CSVs · expected_answer machine-generated not hand-typed · judge_reference authored · derivation_rationale written · no cross-domain duplicates · independently reviewed |
| LLM-as-Judge module | Calibrated to acceptance threshold on ≥10 anchors per domain · non-determinism boundary encoded in the rubric · deterministic settings · full prompt/response logging · rubric PDF delivered |
| Regression scorecard | Baseline established across all five domains · CSV schema stable and CI-consumable · PDF summary generated · regression flag verified against a synthetic 5%-drop test case |
| Documentation | Data dictionary per table · CSV header spec signed off · ER diagram PDF per domain · judge rubric · QA audit report · KT material |

## 14.2  Accuracy gate — all nine conditions before the package ships

- ≥95% deterministic exact-match across all five domains before any final delivery.

- Numeric values identical on repeat runs — no tolerance for numeric drift.

- An independent reviewer, not the developer, re-executes every reference_sql on a clean DuckDB instance.

- Every failed exact-match question is reworked and re-audited. Failing pairs are reworked, never quietly removed from the set.

- Generated SQL logged for every failed question, so the Platform Owner can trace the failure to a pipeline stage.

- Cross-domain uniqueness confirmed: no Q&A question appears in more than one domain.

- Regression scorecard baseline run completed across all five domains.

- Reproducibility confirmed: a clean-room re-run from the seed produces byte-identical CSV output.

- CRM passes the accuracy gate first. Do not advance to final delivery until CRM is certified.

Condition 4 is the one that gets quietly broken Removing a failing pair raises the exact-match percentage without improving anything. It also destroys the benchmark’s value, because the removed questions are exactly the ones the platform finds hard. Pair counts per tier per domain are asserted in CI against the quota in Section 9.1. A drop in count fails the build.

# 15.  QA and Independent Review Protocol

- No self-review. The engineer who authored a dataset or a Q&A pair never audits it. Assignment is recorded in the audit log so independence is demonstrable, not assumed.

- Clean-room execution. The reviewer works from released artefacts only — the exported CSVs and the delivered Q&A files. Not from the author’s branch, notebook, or local environment.

- Full re-execution, not sampling. Every reference_sql is re-executed. Sampling is acceptable only for the qualitative review of judge_reference and derivation_rationale quality, at a minimum of 20% per domain, weighted toward T5.

- Cross-domain uniqueness. Normalise question text (lowercase, strip punctuation and whitespace), hash, and compare across the full corpus. Near-duplicate detection on top of exact hashing, reviewed manually.

- Failure handling. A finding is raised against the pair, returned to the author, reworked, and re-audited by the same reviewer. Findings and resolutions are logged.

- Audit report. Per domain: pairs reviewed, findings raised by category, resolutions, final exact-match rate, anomalies noted, reviewer name and date.

- Reproducibility check. The reviewer performs one full clean-room regeneration from seed per domain and confirms the manifest hashes match.

## 16.1  Week by week

| Wk | Dates | Phase | Focus | Milestone |
| --- | --- | --- | --- | --- |
| 1–2 | 10–21 Aug | P1 Schema design | CRM ER diagram first, then remaining four · validate PK/FK structure per domain · draft DDL · SQLFluff lint · verify join paths · finalise Q&A taxonomy | CRM ER diagram approved · signed CSV header spec · Q&A design spec |
| 2–6 | 17 Aug – 18 Sep | P2 Dataset generation | Build seeded pipeline · CRM generated and delivered first (Wk 3) · engineer distributions per domain · inject imperfections · FK gate · SHA-256 manifest · Git LFS tag | CRM dataset delivered Wk 3 · all five domain CSVs · manifest.json · data dictionaries |
| 3–7 | 24 Aug – 25 Sep | P3 Q&A authoring [concurrent] | CRM Q&A starts Wk 3 on approved dataset · Jinja2 SQL template library T1–T5 · DuckDB verification of every expected_answer · judge_reference authoring · remaining domains follow their dataset by ~1 week | CRM Q&A Wk 4 · all five Q&A files · SQL verification logs |
| 5–8 | 7 Sep – 2 Oct | P4 Judge & scorecard [concurrent] | Build LLM-as-Judge · CRM calibration session with Platform Owner team · apply non-determinism boundary · build scorecard with SQL logging · baseline run on CRM then all domains · begin Orchestrator architecture doc (design only) | Judge module · regression scorecard · baseline accuracy run |
| 9–10 | 5–16 Oct | P5 Audit & handover | Independent reviewer re-executes all reference SQL on clean DuckDB · cross-domain uniqueness check · ≥95% exact-match across all five domains · assemble package · hand to Prime Contractor · support Platform Owner acceptance review | Full package delivered · ≥95% accuracy certified · acceptance sign-off |

## 16.2  Staggered release calendar

Delivery is staggered, not a single Week 10 drop. The first domain is available for client validation inside the agreed Week 2–5 window.

| Domain | Dataset + dictionary | Q&A pairs | Judge calibration | Baseline scorecard |
| --- | --- | --- | --- | --- |
| CRM | Fri 28 Aug (Wk 3) | Fri 4 Sep (Wk 4) | Wk 5 — joint session | Wk 6 |
| Sales | Fri 4 Sep (Wk 4) | Fri 11 Sep (Wk 5) | Wk 6 | Wk 7 |
| Finance | Fri 11 Sep (Wk 5) | Fri 18 Sep (Wk 6) | Wk 7 | Wk 8 |
| Project Management | Fri 18 Sep (Wk 6) | Fri 25 Sep (Wk 7) | Wk 7 | Wk 8 |
| Logistics | Fri 18 Sep (Wk 6) | Fri 25 Sep (Wk 7) | Wk 8 | Wk 8 |

# 18.  Team, Contacts and RACI

## 18.1  Client-side DRIs

| Name | Role | Location | Owns |
| --- | --- | --- | --- |
| Aichi Lin | Senior SDET and team lead | Sunnyvale, USA | Pulse access, API support, evaluation tool support, general support |
| Angela Chen | Software Engineer | Sunnyvale, USA | API support |
| Hao Guan | Software Engineer | Beijing, China | Evaluation tool support; off-hours and India team support |
| Wes Powell | Director of Software Engineering | Sunnyvale, USA | Stakeholder (informed) |
| Evan | Engineering DRI | — | Onboarding, API access, documentation, LLM credentials, data-drop repository |
| Alberto / Rob | Platform side | — | Staging and QA provisioning, PK and metadata structure, internal eval tool demo |

## 18.2  Delivery-side roles

| Role | Responsibility |
| --- | --- |
| Engagement Lead | Client governance, scope control, dependency escalation, commercial interface with the Prime Contractor. Sole owner of any scope conversation. |
| Data Engineering Lead | Generation framework, schema design, distributions, imperfections, integrity gates, manifest and reproducibility. |
| Evaluation Engineer (Q&A) | Tier taxonomy, pair authoring, SQL template library, verification runner, judge reference authoring. |
| LLM / Judge Engineer | Judge module, prompt and rubric design, calibration, scorecard scoring integration. |
| Independent QA Reviewer | Clean-room re-execution, cross-domain uniqueness, audit report, accuracy certification. Must not have authored what they audit. |
| Project Coordinator | Dependency register, status reporting, meeting logistics across Pacific / India / Beijing, milestone tracking. |

## 18.3  RACI

| Workstream | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Schema and ER design | Data Engineering Lead | Engagement Lead | Platform Owner DRI | Prime Contractor |
| Dataset generation | Data Engineering Lead | Engagement Lead | Evaluation Engineer | Platform Owner |
| Q&A authoring | Evaluation Engineer | Engagement Lead | Data Engineering Lead | Platform Owner |
| Judge module and calibration | LLM / Judge Engineer | Engagement Lead | Platform Owner team (CRM session) | Prime Contractor |
| Regression scorecard | LLM / Judge Engineer | Engagement Lead | Evaluation Engineer | Platform Owner |
| QA audit and certification | Independent QA Reviewer | Engagement Lead | All engineers | Prime Contractor, Platform Owner |
| Orchestrator decision | Engagement Lead | Prime Contractor | Platform Owner, End Client | Delivery team |
| Scope changes | Engagement Lead | Prime Contractor | Delivery team | Platform Owner |

# 19.  Dependency Register

Every item here is externally owned. The Project Coordinator maintains status weekly and the Engagement Lead escalates anything red at the weekly sync. Engineers should raise a blocker the day it blocks them, not the day it becomes visible in the schedule.

| ID | Dependency | Owner | Needed by | Status | Impact if missing |
| --- | --- | --- | --- | --- | --- |
| DEP-01 | Engineering DRI named | Client | Week 0 | Done — Evan named | — |
| DEP-02 | Engineer onboarding to Apple Connect | Client (Evan) | Week 1 | Pending — awaiting engineer list submission | Blocks all API access downstream |
| DEP-03 | Pulse API: endpoint, auth, response schema (non-prod) | Client (Evan + DRI) | End Week 1 | Awaiting onboarding | Blocks orchestrator design and any integration testing |
| DEP-04 | API documentation and org-level product access | Client (Evan + DRI) | End Week 1 | Awaiting onboarding | Blocks response-payload handling design |
| DEP-05 | Staging and QA provisioning confirmed | Client (Alberto, Rob) | End Week 1 | Open | No environment to evaluate against |
| DEP-06 | LLM API credentials and usage conditions | Client / Prime | Before Phase 4 | Awaiting onboarding | Blocks judge build and calibration |
| DEP-07 | Confirmed method for loading golden datasets into Pulse | Client (Evan + DRI) | End Week 1 | Partially answered — CSV upload demonstrated; an API route is believed to exist but is unconfirmed | Affects dataset packaging and the evaluation loop design |
| DEP-08 | Data drop repository (S3 or Box) | Client (Evan) | Week 1 | Box link provided but requires internal access we do not hold | No compliant route to deliver artefacts |
| DEP-09 | Primary key and metadata structure for multi-table joins | Client (Rob, Alberto) | Week 0 | Open — client asked what further detail is needed; a working session is offered | Blocks CRM schema confirmation, the first gate of the engagement |
| DEP-10 | Internal evaluation tool demo | End client (Alberto, Rob) | Before Phase 4 | Not scheduled | Orchestrator decision cannot be made; design work stays frozen |
| DEP-11 | Platform Owner participation in CRM judge calibration | Client | Week 5 | To be scheduled | Judge calibration quality degrades for all five domains |
| DEP-12 | Prime Contractor feedback within 5 business days per milestone | Prime | Ongoing | Agreed | Schedule slip; flagged in risk register |

DEP-09 needs closing this week The client’s written response was, in effect, that they are not clear what else is needed and are happy to meet if more examples are required. That is an invitation, and it is going unanswered while CRM schema design sits on the critical path. Action: send a specific, narrow request — the PK/FK structure for the CRM entity set, one worked multi-table join example as Pulse expects it, and confirmation of how join keys surface in the semantic context layer. A vague follow-up will produce another vague answer.

# 20.  Risk Register

| ID | Risk | L | I | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | API access slips past Week 1, compressing everything downstream | M | H | Dataset and Q&A work (Tracks A and B) do not depend on API access — sequence them first. Escalate at the weekly sync from Week 2 if unresolved. |
| R-02 | PK/metadata ambiguity (DEP-09) delays CRM schema, the first gate | M | H | Send the narrow specific request this week; offer a 30-minute working session with Rob and Alberto rather than waiting on written answers. |
| R-03 | Zero numeric tolerance proves unachievable on streamed LLM answers | M | H | Establish early on CRM whether the platform returns stable numerics across repeat runs. If not, this is a platform finding to surface immediately, not a dataset problem to absorb quietly. |
| R-04 | Float and rounding drift in Finance breaks exact match | M | M | Fixed-point decimal internally; rounding defined once and applied identically in generator and reference SQL; explicit precision per column in the data dictionary. |
| R-05 | Orchestrator decision reverses mid-flight and re-enters scope | M | H | Interface-first design during deferral so the scorer is callable from any driver. Any build decision goes through the Engagement Lead as a scope conversation. |
| R-06 | 250K-row tables make DuckDB verification and audit slow | M | M | dev profile at 1% scale for iteration; generate to the smallest honest size per Section 7.3; full verification runs scheduled, not ad hoc. |
| R-07 | Platform agnosticism conflicts with Pulse ingestion in practice | M | M | Agnosticism wins — it is a hard constraint. Any ingestion friction is raised as a client-side finding, with the ANSI-SQL-in-DuckDB test as the neutral arbiter. |
| R-08 | Judge calibration availability across Pacific / India / Beijing | M | M | Book the CRM calibration session in Week 3 for Week 5. Hao Guan in Beijing is the designated off-hours and India-team support route. |
| R-09 | LLM API cost or rate limits during judge runs | L | M | Async batching with backoff; cost tracked per run; credentials and usage conditions confirmed before Phase 4 (DEP-06). |
| R-10 | T1 single-table tier conflicts with the no-single-table rule (OI-1) | M | M | Resolve in writing in Week 1. Until resolved, author T1 pairs but hold them in a separate file so a ruling either way costs one merge, not a rewrite. |
| R-11 | Pairs quietly removed rather than reworked to hit 95% | L | H | CI asserts tier quotas per domain; audit log records every finding and its resolution. |
| R-12 | Scope creep via informal engineer-to-engineer requests | M | M | All scope changes route through the Engagement Lead. Engineers acknowledge and escalate; they do not absorb. |

# 21.  Governance and Communication

| Forum | Cadence | Participants | Purpose |
| --- | --- | --- | --- |
| Client governance sync | Weekly, live | One Tech Lead and one PM per side — deliberately lean | Weekly accomplishments and forward plan. High-level governance only. Not a technical working session. |
| Technical collaboration | Ad hoc | Delivery engineers with Aichi Lin, Angela Chen, Hao Guan as topic requires | Schema questions, API behaviour, payload structure, calibration. Deliberately kept outside the governance sync. |
| Internal delivery standup | Daily, short | Delivery team | Blockers first. Anything externally blocked goes to the dependency register the same day. |
| Milestone review | Per staggered release | Engagement Lead, Prime Contractor, Platform Owner | Artefact walkthrough and acceptance against the Section 14 definition of done. |

Weekly sync timing 6:00 PM Pacific / 6:30 AM India / 9:00 AM Beijing — confirmed workable on the delivery side. Keep it high-level. The value of a lean governance meeting disappears the moment it absorbs technical debugging; route that to the ad hoc channel with the named engineering DRIs.

## 21.1  Weekly status report — fixed format

- Accomplished this week, against the named milestone.

- Planned next week, against the named milestone.

- Dependency register: any item that moved, and any item now red.

- Accuracy position: current exact-match rate per delivered domain.

- Decisions required, with the name of the person who owns each and the date it becomes blocking.

# 22.  Out of Scope

Explicitly outside this engagement. Anything here that becomes desirable is a scope conversation owned by the Engagement Lead, not something absorbed by the delivery team.

- Per-stage pipeline evaluation — scoring intent classification, table selection, or SQL generation independently. SQL capture is for failure diagnosis only.

- Fuzzy or non-exact relationship matching. Scoring is deterministic exact-match or LLM-as-Judge reasoned scoring.

- Model training, fine-tuning, or adaptation of any model on the golden datasets.

- Modification, configuration, debugging, or retraining of any component of the Pulse runtime pipeline.

- FileMaker or MySQL schema design and configuration within the platform. We deliver agreed-header CSV files.

- Production access or any production evaluation run.

- Evaluation Orchestrator implementation — deferred (Section 12), design only.

- Dashboard rendering and styling evaluation. Styling variation is explicitly not a failure.

- Dataset cost optimisation. Accuracy is priority one; cost optimisation is deferred by client agreement.

- Additional domains beyond the five locked. Five fully tuned, not ten partially useful.

- LLM API usage costs for judge scoring — a pass-through, either on client-provided credentials or billed at cost, to be agreed with the Prime Contractor.

# 23.  Open Items Requiring Decision

These are genuinely unresolved. They are not written into the specification as fact, and engineers should not invent an answer. Each has a named owner and a date at which it becomes blocking.

| ID | Open item | Why it matters | Owner | Blocking from |
| --- | --- | --- | --- | --- |
| OI-1 | T1 is a single-table tier at 20% of pairs, but the scope document also states no question should be answerable from a single table | Directly contradictory. Either T1 stays as a deliberate control tier or 20% of every domain’s pairs need redesign. | Engagement Lead → Platform Owner | Week 2 (CRM Q&A authoring) |
| OI-2 | Numeric equality semantics: decimal places, rounding rule, string formatting of returned numbers, thousands separators | Zero tolerance is meaningless without a definition of what "identical" compares. 1000 vs 1,000 vs 1000.00 must be settled. | Evaluation Engineer → Platform Owner DRI | Week 2 |
| OI-3 | Date values returned as answers — exact match, or is any tolerance intended? | Earlier scoring drafts carried a ±1 day tolerance. Current rules imply exact. Affects Project Management and Finance heavily. | Engagement Lead → Platform Owner | Week 3 |
| OI-4 | NULL representation on ingestion — how does the platform interpret an empty CSV field? | If empty is read as an empty string rather than NULL, every T3 LEFT JOIN expected answer is wrong. | Data Engineering Lead → Platform Owner DRI | Week 2 (before CRM generation) |
| OI-5 | Row volume: is 250K per table actually wanted, or is it a ceiling we need not approach? | Materially affects generation, verification, and audit time. Accuracy does not improve above a certain volume. | Engagement Lead → Platform Owner | Week 2 |
| OI-6 | How auto-generated per-source guidelines affect T5 semantic questions | Guidelines are described as generic and low-weight, but they shape how the platform interprets the data. Affects T5 design. | Evaluation Engineer → Platform Owner | Week 4 |
| OI-7 | Data drop mechanism and access (DEP-08) | The provided Box link requires internal access we do not hold. There is no compliant delivery route today. | Project Coordinator → Evan | Week 3 (CRM dataset release) |
| OI-8 | Orchestrator decision date | Twelve hours of design work is committed regardless; a late reversal has a much larger cost and would be a scope conversation. | Prime Contractor → End Client | Week 6 |
| OI-9 | Judge LLM provider, credentials, and cost treatment | Blocks judge build and calibration; also determines whether cost is pass-through or absorbed. | Engagement Lead → Prime Contractor | Week 4 |
| OI-10 | Who consumes the scorecard CSV, and does it need CI/CD integration on the client side? | Determines output stability requirements and whether a schema contract needs versioning. | Engagement Lead → Platform Owner | Week 7 |

# Appendix A  ·  Worked Q&A Pair — CRM

Illustrative example showing all seven fields completed to the expected standard. Use this as the authoring reference.

| Field | Value |
| --- | --- |
| natural_language_question | Which sales rep closed the most deal value last quarter, and how much was it? |
| expected_answer | Priya Raghavan — 4,182,650.00 |
| reference_sql | SELECT a.owner_name, SUM(o.deal_amount) AS total_closed FROM opportunities o INNER JOIN accounts a ON o.account_id = a.account_id WHERE o.stage = 'Closed Won' AND o.close_date >= '2026-04-01' AND o.close_date < '2026-07-01' GROUP BY a.owner_name ORDER BY total_closed DESC LIMIT 1; |
| reference_tables | opportunities, accounts |
| reference_fields | opportunities.account_id, opportunities.deal_amount, opportunities.stage, opportunities.close_date, accounts.account_id, accounts.owner_name |
| judge_reference | The answer should name a single sales rep and state the total closed deal value for the previous quarter. It should make clear that only won deals are counted and that the period is the previous calendar quarter. Presenting the figure with or without currency formatting, and any accompanying explanation of the calculation, are both acceptable. |
| derivation_rationale | Filter opportunities to stage = Closed Won with close_date inside the previous calendar quarter relative to the fixed reference date (2026-08-01), giving 2026-04-01 inclusive to 2026-07-01 exclusive. Join to accounts on account_id to attribute each opportunity to its owning rep. Sum deal_amount per owner_name, order descending, take the top row. Note: two opportunities in this window are near-duplicates from the 1% duplicate injection and are both counted, since the question asks for total closed value rather than distinct deals. |

What makes this example correct The question uses business vocabulary and names no tables or columns. It requires a two-table join — it cannot be answered from opportunities alone, because the rep attribution lives on accounts. The relative time expression is grounded explicitly in the rationale against the fixed reference date, so the answer does not change as real-world time passes. The judge reference describes required substance and explicitly permits formatting variation, in line with HC-3. The rationale surfaces the duplicate-row interaction, which is exactly the kind of detail an auditor needs in order to confirm the answer rather than re-derive it.

# Appendix B  ·  manifest.json Structure

{

"dataset_version": "dataset-v1.0.0",

"domain": "crm",

"generated_at": "2026-08-28T09:14:22",

"reference_today": "2026-08-01",

"seed": 42,

"profile": "full",

"library_versions": { "numpy": "...", "faker": "24.x", "pandas": "2.x", "duckdb": "0.10" },

"files": [

{ "name": "accounts.csv", "sha256": "...", "rows": 24000, "columns": 14 },

{ "name": "opportunities.csv", "sha256": "...", "rows": 186000, "columns": 17 }

],

"imperfections": { "duplicate_pct": 1.0, "null_pct": 2.5, "outlier_pct": 0.5,

"boundary_dates": ["1900-01-01", "2038-01-19", "2099-12-31", "2026-08-01"] },

"integrity": { "fk_check": "passed", "row_cap_check": "passed",

"inner_join_paths_verified": 4, "left_join_unmatched_rows_present": true }

}

# Appendix C  ·  Glossary

| Term | Meaning in this engagement |
| --- | --- |
| Golden dataset | The synthetic relational data the platform is evaluated against. Ground truth lives here. |
| Q&A pair | One natural-language question with its verified deterministic answer and supporting metadata. |
| Judge reference | A model-level ideal answer used to anchor LLM-as-Judge scoring. Describes substance, not phrasing. |
| Exact match | Deterministic comparison of the platform’s answer against expected_answer, with zero numeric tolerance. |
| Non-determinism boundary | The rule separating acceptable variation (phrasing, length, styling) from failure (any numeric variance). |
| Platform agnosticism | The requirement that datasets produce comparable results on any NLQ tooling, not only Pulse. |
| Baseline | The first scorecard run, against which all subsequent runs are compared for regression. |
| Regression flag | Automated alert raised when a domain drops 5 percentage points or more from baseline. |
| Shortcut prevention | Schema design that makes it impossible to answer a join-tier question from a single table. |
| Rephrase group | A set of pairs asking the same underlying question in different surface forms; all must return identical numerics. |